STAGES FOR PROJECTS

Employee Task Assignment

Project Types: CC / RDP / PCC / OC / REVALIDATION

SADHANA

STAGE 1 — File Preparation  —  2 Working Days

- Filing with sticker and basic papers — 7/12, physical survey with surroundings and gutbook superimposed for D.P, gutbook, site photos, KYC questionnaire, Architect Appointment Letter

- Give entire paperwork checklist of approval to client

- Upload project on website

- Give it Office UIN and form WhatsApp group

- Send summarized auto prompt to client and boss on group

STAGE 2 — Paper Procurement  —  5 Working Days

- Prepare 1 office file copy and 1 VVCMC file copy

- Complete balance typing as per entire checklist

- Finalise the file and upload on web

- Forward to Vrushali Madam for online inward

- Forward to Vijay Sir for Legal and Tree NOC (1 set VVCMC hard copy)

- Fast track TILR with client

- Produce rough challan estimate

- Send summarized auto prompt to client and boss on group

UZAID

STAGE 1 — File Preparation  —  2 Working Days (with Sadhana)

- Filing with sticker and basic papers — 7/12, physical survey with surroundings and gutbook superimposed for D.P, gutbook, site photos, KYC questionnaire, Architect Appointment Letter

- Give entire paperwork checklist of approval to client

- Upload project on website

- Give it Office UIN and form WhatsApp group

- Send summarized auto prompt to client and boss on group

STAGE 1 — File Preparation  —  3 Working Days (with Vijay)

- Upload basic plot on DP marking, CRZ, Wetland, Eco Sensitive Zone Corridor, Heritage, KMZ images on website and give remark

- Check whether additional NOCs required (Forest, Railway, Environmental Clearance, Highway Access, etc.) and mention remark accordingly

- Place order for 2 sets of TILR/NOCs — mention date and whether client is doing it or responsible person's name

- Place order for 2 sets of all revenue papers — mention date, whether client is doing it or responsible person's name

- Send summarized auto prompt to document provider, client and boss on group

STAGE 2 — Paper Procurement  —  5 Working Days

- Prepare 1 office file copy and 1 VVCMC file copy

- Complete balance typing as per entire checklist

- Finalise the file and upload on web

- Forward to Vrushali Madam for online inward

- Forward to Vijay Sir for Legal and Tree NOC (1 set VVCMC hard copy)

- Fast track TILR with client

- Produce rough challan estimate

- Send summarized auto prompt to client and boss on group

STAGE 3 — Legal / Tree NOC  —  14 Days upon receipt of TILR and plans from Uday

- Prepare and upload offline drawing

- Ready online clear report and drawing and upload

- Complete final offline docket as per checklist

- Any issues/clarifications to be mentioned to Nihal on live chat window (no verbal communication)

- Ensure Nihal acknowledges offline docket receipt

- Ensure file is inwarded and covering letter with online/offline number is uploaded on site

STAGE 3 — Upon Obtaining Permission

- Update the master file sheet

- Upload all scanning of orders and blueprints

- Forward to Crystal for Rera letters / On-site handling

VIJAY

STAGE 1 — File Preparation  —  3 Working Days

- Upload basic plot on DP marking, CRZ, Wetland, Eco Sensitive Zone Corridor, Heritage, KMZ images on website and give remark

- Check whether additional NOCs required (Forest, Railway, Environmental Clearance, Highway Access, etc.) and mention remark accordingly

- Place order for 2 sets of TILR/NOCs — mention date and whether client is doing it or responsible person's name

- Place order for 2 sets of all revenue papers — mention date, whether client is doing it or responsible person's name

- Send summarized auto prompt to document provider, client and boss on group

STAGE 3 — Legal / Tree NOC  —  21 Working Days

- Mention compliances of legal department and tree department scrutiny periodically

- Confirm and upload final TILR document on web

- Upload final legal and tree NOC signed noting

- Upload DP marking

VRUSHALI

STAGE 2 — Paper Procurement  —  Upon forwarding from Sadhana/Uzaid

- Receive file forwarded for online inward

- Process online inward of the file

STAGE 3 — Legal / Tree NOC  —  14 Days upon receipt of TILR and plans from Uday

- Prepare and upload offline drawing

- Ready online clear report and drawing and upload

- Complete final offline docket as per checklist

- Any issues/clarifications to be mentioned to Nihal on live chat window (no verbal communication)

STAGE 3 — Upon Obtaining Permission

- Update the master file sheet

- Upload all scanning of orders and blueprints

- Handle Rera letters / On-site handling (forwarded from Uzaid)

NIHAL

STAGE 3 — Legal / Tree NOC  —  Upon receipt of offline docket

- Acknowledge that offline docket has been successfully received

- Ensure that file is inwarded

- Upload covering letter with online/offline number identification on the site

UDAY

STAGE 3 — Legal / Tree NOC  —  2 Days

- Attach final signed drawing from client on site for further drafting by Vrushali Madam

CRYSTAL

STAGE 3 — Legal / Tree NOC  —  4 Days

- Attach service drawings and EE report

STAGE 3 — Upon Obtaining Permission

- Handle Rera letters

- On-site handling

GANESH

STAGE 3 — Upon Obtaining Permission  —  Within 2 Days from online permission

- Provide images of notings upon issue of online permission

IMPORTANT NOTES

- All regular prompts should be auto-forwarded to client via WhatsApp regarding stages and incomplete work.

- Auto-forward prompt to Boss after 5 reminders to client.

- Every stage must be summarised with: STATUS (Complete/Pending), Pending With, Clarification, Date of Problem, Communicated To, SS Dates of Email/WhatsApp.